## Stories
Story ID | Story Title | Story Points | Sprint | Priority | Status
1 | Access - Permit Form | 16 | 1, 2 | Must | Closed
2 | Access - Online | 16 | 1, 2 | Should | Closed
3 | Notification - Permit Approval | 2 | 4 | Should | Closed
4 | Access - Physical Approved Permit | 4 | 4 | Must | Closed
5 | Access - Permit Validity | 1 | 3 | Should | Closed
6 | Notification - new Violation | 2 | 4 | Should | Closed
7 | Access - varied Payment Options | 8 | 3 | Must | Closed
8 | Detailed Payment System | 4 | 3 | Must | Closed
9 | Exclusive Staff/Student Permit | 16 | 2 | Should | Closed
10 | Access - Issue Report Forms | 16 | 2 | Must | Closed
11 | Notification - Issue Resolution | 0 | Not to be completed (check priority) | Won't | Closed
12 | Access - Citation Forms | 16 | 2 | Must | Closed
13 | Templates w/ Compulsory Fields | 4 | 2 | Should | Closed
14 | Up-to-date Connection | 8 | 2 | Could | Closed
15 | Access - Portable | 2 | 2 | Should | Closed
16 | Notification - Digital, to violator | 2 | 4 | Must | Closed
17 | Access - Physical Print-out of Violation | 4 | 2 | Must | Closed
18 | Notification - new Permit Request | 2 | 4 | Must | Closed
19 | Automated - create entry “Approval Pending” | 0 | Not to be completed (check priority) | Won't | Closed
20 | Unique - Permit Entry | 1 | 1, 2 | Must | Closed
21 | Organise - Approval Status | 2 | 1, 2 | Must | Closed
22 | Automated - send Notification of Permit Approval | 0 | Not to be completed (check priority) | Won't | Closed
23 | Ensure Physical Permit for Vehicle Owner | 1 | 4 | Must | Closed
24 | Organise - Payment Status | 2 | 1, 2 | Should | Closed
25 | Automated - Overdue Notification | 2 | 4 | Could | Closed
26 | Notification - new H&S Issue | 4 | 4 | Must | Closed
27 | Regular Edits to H&S Issues | 4 | 3 | Should | Closed
28 | Organise - Resolution Status | 2 | 1, 2 | Must | Closed
29 | Upon resolution, enter additional info | 8 | 4 | Must | Closed

## Sprint 1
Day | Hours Remaining | Date Started | Ideal Story Points Remaining | Actual Story Points Remaining | Task Worked | Task ID | Date Completed | Hours Taken to Complete | Hours this sprint | Story Points this sprint
0 | 34.875 | 2016-08-24 | 39 | 39 | Start of Sprint 1 |  |  |  | 34.88 | 39
1 | 34.875 | 2016-08-25 | 36.2143 | 39 | [5 empty] | 1.1183
2 | 34.875 | 2016-08-26 | 33.4286 | 39 |  |  |  |  | 22.875 | 25.5806
3 | 34.875 | 2016-08-27 | 30.6429 | 39
4 | 31.875 | 2016-08-28 | 27.8571 | 35.6452 | Develop Website Template | 8 | 2016-08-28 | 3
5 | 31.875 | 2016-08-29 | 25.0714 | 35.6452 | [5 empty] | 25.5806
6 | 31.875 | 2016-08-30 | 22.2857 | 35.6452
7 | 19.875 | 2016-08-31 | 19.5 | 22.2258 | Develop Dynamic Web Pages | 9 | 2016-09-01 | 12
8 | 18.375 | 2016-09-01 | 16.7143 | 20.5484 | Paper Wireframes | 6 | 2016-09-01 | 1.5
9 | 17.75 | 2016-09-02 | 13.9286 | 19.8495 | Identify Data to be Organised | 12 | 2016-09-02 | 0.625
10 | 17.125 | 2016-09-03 | 11.1429 | 19.1505 | Identify Data to be Organised | 14 | 2016-09-03 | 0.625
11 | 16.5 | 2016-09-04 | 8.3571 | 18.4516 | Identify Data to be Organised | 16 | 2016-09-04 | 0.625
12 | 16.5 | 2016-09-05 | 5.5714 | 18.4516
13 | 12 | 2016-09-06 | 2.7857 | 13.4194 | Identify Required form Fields, Plan UI design and Paper Wireframes | 1,4,7 | 2016-09-06 | 4.5
14 | 12 | 2016-09-07 | 1.1546e-14 | 13.4194

## Sprint 2
Day | Hours Remaining | Date Started | Ideal Story Points Remaining | Actual Story Points Remaining | Task Worked | Task ID | Date Completed | Hours Taken | Hours this sprint | Story Points this sprint
14 | 51.5 | 2016-09-07 | 79.4194 | 79.4194 | Start of Sprint 2 |  |  |  | 79.4194 | 51.5
15 | 45 | 2016-09-08 | 73.7465 | 69.3956 | Access - Permit Form | 1,2,3 | 2016-09-08 | 6.5 |  | 1.5421
16 | 42 | 2016-09-09 | 68.0737 | 64.7692 | Plan & Identify Required Form Fields | 9,14,19 | 2016-09-09 | 3 | 50.5 | 77.8772
17 | 39 | 2016-09-10 | 62.4009 | 60.1428 | UI Design (Wireframe w/Form Details) | 12,17,22 | 2016-09-10 | 3 | 1
18 | 35 | 2016-09-11 | 56.7281 | 53.9743 | Create DB #9 | 10 | 2016-09-11 | 4
19 | 31 | 2016-09-12 | 51.0553 | 47.8058 | Create DB #10 | 15 | 2016-09-12 | 4 |  | 77.8772
20 | 27 | 2016-09-13 | 45.3825 | 41.6373 | Create DB #12 | 20 | 2016-09-13 | 4
21 | 25 | 2016-09-14 | 39.7097 | 38.5531 | Develop UI #9 | 13 | 2016-09-14 | 2
22 | 23 | 2016-09-15 | 34.0369 | 35.4688 | Develop UI #10 | 18 | 2016-09-15 | 2
23 | 21 | 2016-09-16 | 28.3641 | 32.3846 | Develop UI #12 | 23 | 2016-09-16 | 2 |  | 0.64846
24 | 18.5 | 2016-09-17 | 22.6912 | 28.5293 | Organise Status' and check database | 5,6,7,8 | 2016-09-17 | 2.5
25 | 16 | 2016-09-18 | 17.0184 | 24.674 | Search Options | 24 | 2016-09-18 | 2.5
26 | 12 | 2016-09-19 | 11.3456 | 18.5055 | Compulsory Fields and Develop CSS | 4,25 | 2016-09-19 | 4
27 | 6 | 2016-09-20 | 5.6728 | 9.2527 | Configure sign in and connect databases | 26,29 | 2016-09-20 | 6
28 | 1 | 2016-09-21 | -8.8818e-15 | 1.5421 | Test Cases, Provide Web Forms & Connect | 11,16,21,27,31,32 | 2016-09-21 | 5

## Sprint 3
Day | Hours Remaining | Date | Ideal Story Points Remaining | Actual Story Points Remaining | Task Worked | Task ID | Date Completed | Hours Taken to Complete | Hours this sprint | Story Points this sprint
28 | 8.5 | 2016-09-28 | 20 | 20 |  |  |  |  | 20 | 8.5
29 | 8.5 | 2016-09-29 | 18.5714 | 20 | [5 empty] | 2.3529
30 | 3.5 | 2016-09-30 | 17.1429 | 16 | Access - Permit Validity, Access for Dept. Members | 1, 2, 3 | 2016-09-30 | 5 | 14 | 32.9412
31 | 3.5 | 2016-10-01 | 15.7143 | 16
32 | 3.5 | 2016-10-02 | 14.2857 | 16
33 | 3.5 | 2016-10-03 | 12.8571 | 16 | [5 empty] | 20
34 | 3.5 | 2016-10-04 | 11.4286 | 16
35 | 3.5 | 2016-10-05 | 10 | 16
36 | 3.5 | 2016-10-06 | 8.5714 | 16
37 | 3.5 | 2016-10-07 | 7.1429 | 16
38 | 3.5 | 2016-10-08 | 5.7143 | 16
39 | 3.5 | 2016-10-09 | 4.2857 | 16
40 | 3.5 | 2016-10-10 | 2.8571 | 16
41 | -1.5 | 2016-10-11 | 1.4286 | 12 | Edit data - Health & Safety | 4 | 2016-10-11 | 5
42 | -5.5 | 2016-10-12 | 0 | 0 | Payment System - Payment Page and Tracking | 5,6,7,8 | 2016-10-12 | 4

## Sprint 4
Day | Hours Remaining | Date | Ideal Story Points Remaining | Actual Story Points Remaining | Task Worked | Task ID | Date Completed | Hours Taken to Complete | Hours this sprint | Story Points this sprint
42 | 23.5 | 2016-10-12 | 24 | 24 |  |  |  |  | 24 | 23.5
43 | 23.5 | 2016-10-13 | 22.2857 | 24 | [5 empty] | 1.0213
44 | 23.5 | 2016-10-14 | 20.5714 | 24 |  |  |  |  | 23.5 | 24
45 | 23.5 | 2016-10-15 | 18.8571 | 24
46 | 23.5 | 2016-10-16 | 17.1429 | 24
47 | 23.5 | 2016-10-17 | 15.4286 | 24 | [5 empty] | 24
48 | 23.5 | 2016-10-18 | 13.7143 | 24
49 | 23.5 | 2016-10-19 | 12 | 24
50 | 23.5 | 2016-10-20 | 10.2857 | 24
51 | 23.5 | 2016-10-21 | 8.5714 | 24
52 | 23.5 | 2016-10-22 | 6.8571 | 24
53 | 16.5 | 2016-10-23 | 5.1429 | 16.8511 | Access, Physical Permit, Resolution + Info | 5,6,16,17,24,25 | 2016-10-25 | 7
54 | 6.5 | 2016-10-24 | 3.4286 | 6.6383 | Notifications | 1-4, 18-23 | 2016-10-25 | 10
55 | 0 | 2016-10-25 | 1.7143 | 0 | Notifications | 7-15 | 2016-10-25 | 6.5
56 | 0 | 2016-10-26 | 0 | 0

## Release
Release | Sprint | Ideal Story Points Remaining | Actual Story Points Remaining | Planned Story Points Remaining | Velocity (Story Points)
1 | Start | 149 | 149 | 149
| 1 | 111.75 | 123.4194 | 110 | 25.5806
| 2 | 74.5 | 44 | 52 | 79.4194
2 | 3 | 37.25 | 24 | 12 | 20
| 4 | 0 | 0 | 0 | 24